## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | User Profile Management | As a TA, I want to create and update my professional profile and CV path, so that Module Organisers can review my qualifications. | Must | 1 | 1. System captures Name, ID, and Skills. | 5 | GUI: Profile Form
[5 empty] | 2. Validates PDF path format. |  | Storage: Save to profiles.json
[5 empty] | 3. Duplicate ID check: show error if profile exists. |  | Logic: Input validation.
US02 | Job Posting | As a Module Organiser (MO), I want to post TA vacancies with specific requirements, so that students can find them. | Must | 1 | 1. Input fields for Module Name, Required Skills, and Weekly Hours. | 3 | GUI: Job Creation Dialog
[5 empty] | 2. Jobs are saved with a unique Job ID. |  | Storage: Append to jobs.json.
US03 | Data Persistence Engine | As a System, I want to store all data in text-based formats (JSON/CSV), so that the system functions without a database. | Must | 1 | 1. Data persists after application restart. | 8 | Backend: DAO Pattern implementation.
[5 empty] | 2. Error handling for corrupted or missing files. |  | Tech: Use javax.json or Gson for parsing.
3. Successful Read/Write operations for all entities.
US04 | Application Tracking | As a TA, I want to view the real-time status of my applications, so that I know if I have been hired or rejected. | Must | 1 | 1. Status reflects MO's decisions instantly. | 2 | GUI: Student Dashboard
[5 empty] | 2. List view of all applied modules with current status. |  | Logic: Filter applications.json by Student_ID.
US05 | Job Discovery & Application | As a TA, I want to browse available jobs and submit applications, so that I can apply for suitable roles. | Must | 2 | 1. Display only 'Open' status jobs. | 5 | GUI: Job List View
[5 empty] | 2. Prevent double application for the same job. |  | Logic: Create record in applications.json.
3. Confirmation message after submission.
US06 | Applicant Selection | As a MO, I want to accept or reject applicants for my modules, so that I can finalize my teaching team. | Must | 2 | 1. View list of applicants per job. | 3 | GUI: Application Review Panel
[5 empty] | 2. Update application status to 'Accepted' or 'Rejected'. |  | Logic: Status transition logic.
3. Update job status to 'Filled' if quota met.
US07 | Workload Monitoring | As an Admin, I want to monitor the total weekly hours of each TA, so that nobody exceeds the 20-hour limit. | Should | 2 | 1. Aggregate hours across all 'Accepted' jobs for a TA. | 5 | Logic: Workload calculation service.
[5 empty] | 2. Visual warning (Red color) if hours > 20. |  | GUI: Admin Dashboard with alerts.
3. Block new 'Acceptance' if it causes overload.
US08 | AI Skill Matching | As a MO, I want to see a matching score for each applicant, so that I can identify the most qualified candidates efficiently. | Should | 3 | 1. Calculate similarity between TA skills and Job requirements. | 5 | AI Feature: Simple String/Set matching algorithm.
[5 empty] | 2. Display score as a percentage (0-100%). |  | Note: No external AI APIs used.
US09 | Missing Skill Identification | As a TA, I want to see which required skills I am missing for a specific job, so that I can improve my profile. | Could | 3 | 1. Compare TA skill set with Job requirement set. | 3 | AI Feature: Set difference logic (Job_Skills - TA_Skills).
2. List missing keywords in the job details view.